## Sheet1
Project Name: |  | Event Board |  |  |  |  | Beta Testers | Sri Charan
Team Member |  | Muni Lohith Krishna Mohan Konidala |  |  |  |  | Beta Testers | Manish Reddy
Team Member |  | Shruti Ramesh Babu Mallavolu |  |  |  |  | Beta Testers | Rohan
Team Member |  | Muneer Ahmed
Release Date:
Item | Acceptance criteria or Requirement |  | Test Type | Owner or Responsible | Priority | Test Result | Comments
1 | Null Input |  | All pages | Alpha Testing | High | Accept | Popup's up "Please enter valid username and password"
2 | Invalid Input |  | Login Page, User, Association registeration page | Alpha Testing | High | Accept | Popup's up "Please enter valid username and password"
3 | Correct input for user |  | Login Page | Alpha Testing | High | Accept | Refer Alpha_testing_report
4 | Correct input for approved association |  | Login Page | Alpha Testing | High | Accept
5 | Correct input for unapproved association |  | Login Page | Alpha Testing | High | Accept
6 | Correct input for admin |  | Login Page | Alpha Testing | High | Accept | Refer Alpha_testing_report
7 | Logging in as association |  | Login Page | Alpha Testing | High | Reject | Refer Alpha_testing_report
8 | Already existing userid |  | User, Association Registration Page | Alpha Testing | Moderate | Accept | Refer Alpha_testing_report
9 | Mismatch password and verify password |  | User, Association Registration Page | Alpha Testing | Moderate | Accept | Refer Alpha_testing_report
10 | Back button |  | User, Association Registration Page | Alpha Testing | Moderate | Accept
11 | Invalid character inputs |  | User Registration Page | Alpha Testing | Moderate | Reject | Refer Alpha_testing_report
12 | Invalid character inputs |  | Association Registration Page | Alpha Testing | Moderate | Reject | Refer Alpha_testing_report
13 | Button clicks |  | All homepages | Alpha Testing | Low | Accept | Refer Alpha_testing_report
14 | Related panels and pages(like Profile, events panel etc) |  | All homepages | Alpha Testing | Low | Accept
15 | Initial Test |  | All homepages | Alpha Testing | Low | Accept | Popup's up the Home Panel
16 | Following an event/association |  | User home page | Alpha Testing | Low | Accept | Gives popup "Followed the association: Umass SASA"
17 | Unfollowing an event/association |  | User home page | Alpha Testing | Low | Accept | Gives popup "Unfollowed the association: Umass SASA"
18 | Creating a new event |  | Association home page | Alpha Testing | Moderate | Accept | Gives popup "Succesfully created an event!"
19 | Approving an association |  | Admin home page | Alpha Testing | Moderate | Accept | Gives popup “Approved associationName”
20 | Rejecting an association |  | Admin home page | Alpha Testing | Moderate | Accept | Gives popup “Rejected associationName”
21 | Exiting the application |  | All pages | Alpha Testing | Moderate | Accept | Exits the application and closes all the jFrame’s
22 | Logout |  | All pages | Alpha Testing | High | Accept | Logs the user out and returns back to the login page
23 | User Charan |  |  | Beta Testing
24 | User Rohan |  |  | Beta Testing
25 | User Manish |  |  | Beta Testing